## Bug Log
Bug ID | Summary | Module | Severity | Priority | Status | Reported | Closed | Lifecycle History (Open → ... → Closed)
DBQA-101 | Full 16-digit credit card number is displayed in clear text on the purchase confirmation dialog | Checkout / Payment | Critical | Highest | Closed | 09 Sep 2026 | 12 Sep 2026 | Open (09 Sep) → In Progress (09 Sep) → Fixed (11 Sep) → Retest (12 Sep) → Closed (12 Sep)
DBQA-102 | Order is accepted with an arbitrary non-numeric credit card value (no length or Luhn validation) | Checkout / Payment | Critical | Highest | Closed | 09 Sep 2026 | 13 Sep 2026 | Open (09 Sep) → In Progress (10 Sep) → Fixed (12 Sep) → Retest (12 Sep) → Closed (13 Sep)
DBQA-103 | Checkout can be completed from an empty cart, creating a confirmed order with an amount of 0 USD | Checkout / Cart | Critical | High | Closed | 09 Sep 2026 | 13 Sep 2026 | Open (09 Sep) → In Progress (10 Sep) → Fixed (12 Sep) → Retest (13 Sep) → Closed (13 Sep)
DBQA-104 | Checkout accepts an impossible expiry month (13) and a long-expired expiry year (1999) | Checkout / Payment | Major | High | Closed | 10 Sep 2026 | 13 Sep 2026 | Open (10 Sep) → In Progress (10 Sep) → Fixed (12 Sep) → Retest (13 Sep) → Closed (13 Sep)
DBQA-105 | Place Order form validates only Name and Credit card - Country, City, Month and Year may be left blank | Checkout | Major | Medium | Closed | 10 Sep 2026 | 14 Sep 2026 | Open (10 Sep) → In Progress (11 Sep) → Fixed (13 Sep) → Retest (14 Sep) → Closed (14 Sep)
DBQA-106 | Login failure messages disclose whether a username exists (account enumeration) | Authentication | Major | High | Closed | 08 Sep 2026 | 12 Sep 2026 | Open (08 Sep) → In Progress (09 Sep) → Fixed (11 Sep) → Retest (12 Sep) → Closed (12 Sep)
DBQA-107 | No account lockout or rate limiting - 100 consecutive failed login attempts are accepted | Authentication | Major | High | Deferred | 08 Sep 2026 |  | Open (08 Sep) → In Progress (09 Sep) → Deferred (14 Sep)
DBQA-108 | Registration enforces no password policy - an account is created with the password '1' | Registration | Major | Medium | Closed | 07 Sep 2026 | 12 Sep 2026 | Open (07 Sep) → In Progress (09 Sep) → Fixed (11 Sep) → Retest (12 Sep) → Closed (12 Sep)
DBQA-109 | Username is not trimmed on registration, allowing near-duplicate accounts (' jayant_qa01 ') | Registration | Minor | Low | Open | 14 Sep 2026 |  | Open (14 Sep)
DBQA-110 | Cart does not aggregate quantity - adding the same product twice creates two separate line items | Shopping Cart | Major | High | Closed | 08 Sep 2026 | 16 Sep 2026 | Open (08 Sep) → In Progress (09 Sep) → Fixed (11 Sep) → Retest (12 Sep) → Reopened (12 Sep) → In Progress (13 Sep) → Fixed (15 Sep) → Retest (15 Sep) → Closed (16 Sep)
DBQA-111 | Cart total is not recalculated after an item is deleted until the page is manually refreshed | Shopping Cart | Major | High | Closed | 08 Sep 2026 | 16 Sep 2026 | Open (08 Sep) → In Progress (09 Sep) → Fixed (11 Sep) → Retest (12 Sep) → Reopened (13 Sep) → In Progress (13 Sep) → Fixed (15 Sep) → Retest (15 Sep) → Closed (16 Sep)
DBQA-112 | Cart contents are not cleared on logout and remain visible to the next user of the same browser | Shopping Cart | Major | Medium | Closed | 11 Sep 2026 | 14 Sep 2026 | Open (11 Sep) → In Progress (11 Sep) → Fixed (13 Sep) → Retest (14 Sep) → Closed (14 Sep)
DBQA-113 | Product page offers no quantity selector - each unit requires a separate Add to cart round trip | Product Details | Minor | Medium | Deferred | 09 Sep 2026 |  | Open (09 Sep) → In Progress (11 Sep) → Deferred (15 Sep)
DBQA-114 | 'Add to cart' confirmation uses a native browser alert that blocks the page until dismissed | Product Details | Minor | Low | Closed | 09 Sep 2026 | 16 Sep 2026 | Open (09 Sep) → In Progress (12 Sep) → Fixed (15 Sep) → Retest (16 Sep) → Closed (16 Sep)
DBQA-115 | Catalogue provides no search capability - products can only be found by browsing categories | Product Catalogue | Major | Medium | Deferred | 08 Sep 2026 |  | Open (08 Sep) → In Progress (10 Sep) → Deferred (14 Sep)
DBQA-116 | 'Next' pagination control renders an empty product grid when the last page has been reached | Product Catalogue | Minor | Medium | Closed | 08 Sep 2026 | 13 Sep 2026 | Open (08 Sep) → In Progress (10 Sep) → Fixed (12 Sep) → Retest (13 Sep) → Closed (13 Sep)
DBQA-117 | 'Previous' pagination control is enabled on the first page and performs no action when clicked | Product Catalogue | Trivial | Low | Closed | 08 Sep 2026 | 13 Sep 2026 | Open (08 Sep) → In Progress (10 Sep) → Fixed (12 Sep) → Retest (13 Sep) → Closed (13 Sep)
DBQA-118 | Contact Us form is submitted successfully with an invalid email address and an empty message | Contact Us | Minor | Medium | Closed | 10 Sep 2026 | 15 Sep 2026 | Open (10 Sep) → In Progress (12 Sep) → Fixed (14 Sep) → Retest (15 Sep) → Closed (15 Sep)
DBQA-119 | Price formatting differs between the product page ('$360') and the cart table ('360') | Product Details / Cart | Trivial | Low | Closed | 11 Sep 2026 | 14 Sep 2026 | Open (11 Sep) → In Progress (12 Sep) → Rejected (14 Sep) → Closed (14 Sep)
DBQA-120 | Place Order modal action buttons are cut off below the fold at viewport widths of 480px and under | Checkout | Major | Medium | Closed | 12 Sep 2026 | 16 Sep 2026 | Open (12 Sep) → In Progress (13 Sep) → Fixed (15 Sep) → Retest (16 Sep) → Closed (16 Sep)
DBQA-121 | Session never expires - an idle authenticated session is still valid after 12 hours | Authentication | Major | Medium | In Progress | 15 Sep 2026 |  | Open (15 Sep) → In Progress (16 Sep)
DBQA-122 | Home page Largest Contentful Paint is 6.2s on simulated Fast 3G due to uncompressed product images | Performance | Minor | Medium | Deferred | 15 Sep 2026 |  | Open (15 Sep) → In Progress (16 Sep) → Deferred (16 Sep)
Total defects logged: | 22
By severity: | Critical: 3 ¦ Major: 11 ¦ Minor: 6 ¦ Trivial: 2
By status: | Closed: 16 ¦ Deferred: 4 ¦ Open: 1 ¦ In Progress: 1